## Slide 1
Greenfield DC Program
WMS / WCS / Automation Go-Live
Monthly Leadership Report-Out
Reporting period: Month 1 — Initiation | Program status: GREEN | Prepared for: Fulfillment Leadership / SVP Review
Prepared by: Program Management Office | Confidential — internal use only
Notes: Two-minute opening: program is Green at the end of Initiation; charter, budget and governance approved; two decisions are needed today (vendor contract release and Wi-Fi scope change). Everything in this deck is generated from the Tracking Playbook dashboard.

## Slide 2
Executive summary
One page: where we are, what changed, what we need from you
GREEN
Overall program status: ON TRACK. Initiation phase 71% complete; Gate 1 closes next week. 388 days to target go-live (03-Oct-27). Budget forecast +1.9% vs. approved (within ±5% tolerance).
Accomplished this month
Charter, budget baseline ($45.5M) and governance model approved by sponsor
Stakeholder register and RACI established — 20 leads, 81 tasks traced to 8 objectives
Integrated master plan drafted; critical path runs through MHE manufacture → install → throughput test
Permit pre-submission meeting booked (action closed)
Watch items
MHE vendor lead-time risk (High) — component shortages could move install by 2–4 weeks
Wi-Fi coverage gaps in mezzanine (High issue) — design revision in progress, +$0.3M
Permit approval timing (Medium) — mitigated via expediter and pre-submission review
7 open RAID items, all owned and dated; 2 open actions, none overdue
Decisions needed today
Release MHE and WMS vendor contracts ($24.5M committed) to lock manufacturing slots
Approve Wi-Fi design change (+$0.3M from contingency)
Confirm early recruiting start (4 weeks ahead) to de-risk go-live staffing
Endorse AI Copilot use for status, RAID and gate audits across the program
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
2
Notes: Read the banner, then the three columns left to right. Spend most of the time on the decisions column — the rest of the deck is backup.

## Slide 3
Program at a glance
Live KPIs from the Tracking Playbook dashboard
388
days to go-live
Target 03-Oct-27
6%
tasks complete
5 of 81 tasks; 3 in progress
0
tasks overdue
0 at risk, 0 blocked
7
open RAID items
2 High severity — see Risks
+1.9%
budget forecast vs. plan
$46.4M FAC vs. $45.5M approved
1 / 8
gates passed (pending)
Gate 1: 5 of 6 items complete
Health legend: Green = on plan · Amber = needs attention / decision · Red = off plan. Budget figures are illustrative pending Finance close.
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
3
Notes: Every number here maps to a Dashboard cell. The 6% complete is expected — we are one month into a twelve-month program; the meaningful signals are zero overdue and the two High RAID items.

## Slide 4
Progress by phase
Task completion against the 81-task master plan — stacked by status
Chart: Tasks by phase and status
| 1. Initiation | 2. Planning & Design | 3. Build & Configure | 4. Site Readiness | 5. Integration & Testing | 6. Training & Change | 7. Cutover & Go-Live | 8. Hypercare & Close
Complete | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
In Progress | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Not Started | 0 | 15 | 17 | 9 | 9 | 7 | 9 | 7
What this tells us
Initiation is 71% complete (5 of 7); Gate 1 review and vendor shortlist finish this week
Planning & Design has started early — integrated master plan is in progress ahead of Gate 1 closure
Build & Configure (17 tasks) and Planning & Design (16) carry 41% of all work — the next two quarters are the heaviest
No task is overdue, at risk or blocked; health is Green across all active tasks
Critical path: MHE manufacture (wk 12–24) → install (wk 26–32) → throughput test (wk 34–37) → go-live (wk 44)
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
4
Notes: Native chart — data is copied from the Dashboard phase table. Point out that the two largest phases are next, which is why vendor contract release today matters.

## Slide 5
Gate roadmap to go-live
Eight Completeness Gates — a phase cannot close with open checklist items
G1
Initiation
01-Nov-26
G2
Design
27-Dec-26
G3
Build
04-Apr-27
G4
Site ready
06-Jun-27
G5
Testing
11-Jul-27
G6
People ready
25-Jul-27
G7
Go-live
15-Aug-27
G8
Close
03-Oct-27
Today (Month 1)
Key milestones on the critical path
Vendor contracts executed
Dec-26
MHE equipment on site
Mar-27
Certificate of occupancy
Jun-27
Throughput acceptance ≥95%
Jul-27
Go / No-Go decision
Aug-27
Production go-live
Aug-27
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
5
Notes: Gate 1 is amber only because the vendor shortlist item is still in progress; it closes at next week's steering committee. All other gates are future.

## Slide 6
OKR scorecard
Charter objectives, key results and current status — traced to tasks in the master plan
Objective | Key result / measure | Tasks | Progress | Status
OBJ-01 Open the greenfield DC on schedule | Production go-live by 03-Oct-27; cutover within window | 15 | 27% | On Track
OBJ-02 WMS / WCS stack with no Sev-1 at go-live | Zero open Sev-1 at go / no-go; SIT and UAT exit criteria met | 20 | 0% | On Track
OBJ-03 Automation at design throughput | Throughput acceptance ≥ 95% of design rate | 9 | 0% | At Risk
OBJ-04 Trained, certified workforce before first receipt | 100% of go-live associates certified; supervisors signed off | 11 | 0% | On Track
OBJ-05 Site, safety and regulatory readiness | Certificate of occupancy; fire, OSHA, equipment sign-offs | 7 | 0% | On Track
OBJ-06 Inbound / outbound network connected | EDI partners live; carriers onboarded; first shipments executed | 11 | 0% | On Track
OBJ-07 Deliver within approved budget | Actual spend within ±5% of $45.5M at close | 4 | 25% | On Track
OBJ-08 Stabilise and hand over to run | Hypercare exit met; lessons learned published | 4 | 0% | On Track
OBJ-03 flagged At Risk by PMO judgement (tracker shows On Track): the High-severity MHE lead-time risk (R-001) sits directly on the throughput objective. Contract release today is the mitigation.
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
6
Notes: Progress % = tasks complete / tasks linked, from the Objectives sheet. Be transparent that the tracker formula says On Track for OBJ-03 and the PMO is overriding to At Risk based on the open High risk.

## Slide 7
Workstream health
Leads, load and status across the 13 active workstreams
Workstream | Tasks | Done / In prog. | Health | Focus this month
PMO | 16 | 4 / 2 | Green | Gate 1 close, master plan baseline
Integration & Data | 9 | 0 / 0 | Green | Interface catalogue starts Nov
Operations & Staffing | 8 | 0 / 0 | Amber | Early recruiting decision needed
Automation (MHE) | 6 | 0 / 0 | Amber | Vendor lead-time risk; contract release
Change & Training | 5 | 0 / 0 | Green | Change plan due Dec
Testing | 5 | 0 / 0 | Green | Test strategy due Dec
Site Readiness | 4 | 0 / 0 | Green | Permits in pre-submission
Transportation | 4 | 0 / 0 | Green | Design starts Nov
Cutover & Go-Live | 4 | 0 / 0 | Green | Not yet active
Vendors | 3 | 0 / 1 | Amber | Shortlist closing; contracts to sign
Finance | 3 | 1 / 0 | Green | Baseline approved; monthly capex review
Infrastructure | 3 | 0 / 0 | Amber | Wi-Fi gap issue (I-005)
Hypercare & Close | 3 | 0 / 0 | Green | Not yet active
Chart: Workstreams by health
| Green | Amber | Red
Health | 9 | 4 | 0
Amber drivers
MHE lead time (R-001)
Wi-Fi coverage (I-005)
Go-live hiring (R-006)
Vendor contract timing
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
7
Notes: Health is a PMO assessment combining tracker status with open RAID items — amber workstreams each have one High/Medium risk or an open decision, not slipped tasks.

## Slide 8
Top risks and issues
From the RAID log — 7 open items, ranked by probability × impact
ID | Type | Description | Owner | Score | Response / mitigation | Due
R-001 | Risk | MHE vendor manufacturing lead time may slip (component shortages) | Automation Lead | 15 High | Weekly vendor milestone review; alternate drive suppliers; 2-week schedule buffer | 28-Dec-26
I-005 | Issue | Wi-Fi survey found coverage gaps in mezzanine area | IT Infra Lead | 15 High | Add access points to design; revise budget (+$0.3M) — decision requested | 07-Dec-26
D-004 | Dependency | WMS SIT depends on vendor WCS emulation model | QA / Test Mgr | 12 Med | Contractual milestone; fallback manual stubs if late | 05-Apr-27
R-006 | Risk | Local labour market may not support go-live hiring plan | Operations Lead | 12 Med | Recruit 4 weeks earlier; agency backup; referral programme — decision requested | 03-May-27
R-002 | Risk | Permit approval delays could push construction start | Facilities Lead | 8 Med | Pre-submission meeting booked; expediter engaged | 30-Nov-26
Chart: Open RAID by severity (7)
| High | Medium | Low
Open RAID | 2 | 3 | 2
Not shown: A-003 ERP standard APIs (Low, validating in design workshop) and D-007 carrier TMS lanes before EDI test (Low, sequenced). All 7 items have an owner and due date; none overdue. Two High items are the only ones requiring leadership decisions.
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
8
Notes: Lead with R-001 and I-005 — both are resolved by the decisions on slide 10. The rest are managed inside the program.

## Slide 9
Budget and forecast
Approved $45.5M capex baseline — illustrative figures pending Finance month-end close
Chart: Approved vs. committed vs. spent by category ($M)
| Building & site fit-out | MHE automation | WMS / WCS software & services | IT infrastructure | Integration & data | Staffing, training & change | PMO & contingency
Approved | 12 | 18.5 | 6 | 2.5 | 1.5 | 2 | 3
Committed | 4.2 | 14.8 | 4.6 | 0.6 | 0.3 | 0.1 | 0.4
Spent to date | 0.9 | 0.4 | 0.5 | 0.1 | 0.05 | 0.05 | 0.1
$45.5M
Approved baseline
$25.0M
Committed (55%)
$2.1M
Spent to date (5%)
$46.4M
Forecast at completion
+$0.9M
Variance (+1.9%)
Variance driver | $M | Status
MHE — expedite fee to protect manufacturing slot (R-001) | +0.6 | Provisional
IT infrastructure — additional Wi-Fi access points (I-005) | +0.3 | Decision requested
Funded from PMO & contingency ($3.0M) — remaining after both | 2.1 | Within tolerance
Ask: release $24.5M vendor commitments (MHE $14.8M, WMS $4.6M, construction $4.2M, other $0.9M) this month to hold manufacturing and install slots. Delay of one month moves go-live risk from Amber to Red.
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
9
Notes: All budget figures are sample values for the report-out format; replace with Finance actuals each month. The structure — approved, committed, spent, forecast, variance drivers — should stay the same so the SVP audience sees the same shape every month.

## Slide 10
Decisions needed from leadership
Four decisions; each has a recommendation and a cost of delay
1
Release MHE and WMS vendor contracts ($24.5M)
Recommend: APPROVE now.
Locks manufacturing slot and install window; mitigates R-001. Each month of delay moves go-live by ~1 month.
Sponsor / Finance
2
Approve Wi-Fi design change (+$0.3M from contingency)
Recommend: APPROVE.
Closes High issue I-005 before network install; contingency remains $2.1M after all known variances.
Sponsor / IT
3
Start go-live recruiting 4 weeks early (Mar-27 vs. Apr-27)
Recommend: APPROVE.
Adds ~$0.1M opex; removes the largest people risk (R-006) ahead of training and dress rehearsal.
Operations / HR
4
Endorse AI Copilot for status, RAID and gate audits program-wide
Recommend: APPROVE (pilot already in use by PMO).
Cuts reporting effort 40–50%; every gate audited against checklist so nothing is missed. No incremental cost — existing licences.
SVP Fulfillment
10
Notes: This is the slide to get to within five minutes. Ask for each decision explicitly and record the outcome in the Action Log before leaving the room.

## Slide 11
Recommended path forward — next 30 days
What the program will deliver by the next report-out
Close out Initiation
Pass Gate 1 at steering committee (vendor shortlist complete)
Baseline the integrated master plan and RAID log
Execute vendor contracts on approval
Launch Planning & Design
Facility design and permit submissions
WMS fit-gap workshops start; functional design by Dec
Automation layout and throughput model
Interface catalogue and data migration strategy
Retire the two High items
R-001: vendor milestone plan and alternate drive suppliers confirmed
I-005: revised Wi-Fi design issued; APs ordered
Weekly exception review on all RAID items
Scale the AI Copilot
Gate 2 checklist audit automated
Weekly status drafted from the tracker dashboard
Meeting actions captured to Action Log automatically
Next report-out (Month 2): Gate 1 passed, contracts executed, Planning & Design ≥ 40% complete, both High RAID items downgraded or closed, budget forecast refreshed with Finance actuals.
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
11
Notes: These are the commitments the PMO is making for next month — they become the first slide of the next report-out.

## Slide 12
Appendix — Gate 1 checklist and open actions
Detail behind the Initiation status
Gate 1 — Initiation checklist | Status
Project charter approved by sponsor | Complete
Budget baseline approved and funding released | Complete
Stakeholder register complete with escalation paths | Complete
Steering committee cadence and RAID log established | Complete
Gate checklists and templates loaded into PM tool / AI Copilot | Complete
Vendor shortlist and SOW status confirmed | In Progress
Gate status: OPEN — 1 item (5 of 6 complete). Expected to pass 01-Nov-26.
Action | Owner | Due | Status
Confirm alternate supplier options for conveyor drives | Procurement | 02-Nov-26 | Open
Circulate revised Wi-Fi design with additional access points | IT Infra | 29-Oct-26 | In Progress
Book pre-submission meeting with permitting authority | Facilities | 30-Oct-26 | Complete
How this report is produced
Single source: the Greenfield Tracking Playbook workbook (Dashboard, Master Plan, RACI, Gate Checklists, RAID, Action Log)
Owners update status weekly; the AI Copilot flags stale tasks, drafts the status narrative and audits gate checklists
PMO reviews exceptions only; PM approves every number before it reaches this deck
Same structure every month: summary → KPIs → phase → OKRs → workstreams → risks → budget → decisions → next 30 days
Budget figures shown are illustrative until replaced with Finance actuals
Greenfield DC — WMS / WCS / Automation Go-Live | Monthly Leadership Report-Out | Source: Tracking Playbook (Dashboard, Master Plan, RAID Log)
12
Notes: Backup slide — use only if asked about Gate 1 detail or how the numbers are produced.