## Read Me
Greenfield Supply Chain Go-Live — End-to-End Tracking Playbook
Companion to the 'AI-Enabled Project Execution for Supply Chain' proposal. One workbook, one source of truth, from initiation to production go-live and close.
HOW TO USE
1. Stakeholders | Start here. Confirm names, roles and escalation contacts. IDs (SH-xx) are used everywhere else.
2. Objectives | Charter objectives and success criteria. Every task traces to one objective; objective status rolls up automatically.
3. Master Plan | The integrated plan and traceability matrix: 81 pre-loaded tasks across 8 phases and 13 workstreams. Update Status, % Complete, Evidence and Notes weekly. Add rows as needed — dropdowns and formulas extend to row 200+.
4. RACI Matrix | Auto-generated grid of every stakeholder against every task (R/A/C/I), with load totals. Do not edit — change assignments in the Master Plan.
5. Gate Checklists | Completeness Gate items per phase. A gate shows PASSED only when every item is Complete or N/A. Review before each gate meeting.
6. RAID Log | Risks, Assumptions, Issues, Dependencies with scoring, owners and due dates. Link each entry to a task.
7. Action Log | Meeting actions with owners and due dates. Overdue days calculate automatically.
8. Dashboard | Executive view: overall progress, phase and workstream status, gate status, stakeholder load. Fully formula-driven — nothing to type.
LEGEND
Blue text | Input — type here.
Grey fill | Formula — do not edit.
Yellow fill | Key assumption or field you must set (project name, start date).
Health colours | Green = on track · Amber = at risk / overdue / late start · Red = blocked or > 5 days overdue · Grey = done.
WEEKLY ROUTINE (with AI Copilot)
Monday | Owners update Status / % Complete / Evidence in Master Plan. Copilot flags tasks with no update in 7 days.
Tuesday | PMO reviews Dashboard exceptions only: overdue, at risk, blocked, unowned RAID items, open gate items.
Wednesday | Copilot drafts status report from Dashboard; PM reviews and sends. Meeting actions captured into Action Log.
Gate week | Copilot audits the Gate Checklist and lists gaps; PM confirms; sponsor approves gate at steering committee.
ASSUMPTIONS
Dates | Example plan assumes a 52-week programme starting 05-Oct-2026 (Dashboard B5). All task dates are example inputs — replace with your baseline.
Example data | Rows marked Complete / In Progress in Master Plan, RAID Log and Action Log are illustrative examples showing the expected format.
Phases | Phases follow the five AI Copilot moments (Intake, Plan, Monitor, Communicate, Close) mapped to a greenfield DC lifecycle.

## Dashboard
Greenfield Supply Chain Go-Live — Executive Dashboard
All figures calculate from the tracking sheets. Nothing to edit here except the project name and dates in the blue cells.
Project | Greenfield DC — WMS / WCS / Automation Go-Live
Project start | 2026-10-05
Target go-live | 2027-10-03
Report date | 2026-09-11
Days to go-live | 387
| Total tasks | Complete | % Complete | In progress | At risk / blocked | Overdue tasks | Open RAID items | High-severity RAID | Open actions
| 81 | 5 | 6.173% | 3 | 0 | 0 | 7 | 2 | 2
Progress by phase
Phase | Tasks | Complete | % Complete | In Progress | At Risk / Blocked | Overdue | Phase Start | Phase Due | Gate Status
1. Initiation | 7 | 7 | 100% | 0 | 0 | 0 | 2026-10-05 | 2026-11-01 | PASSED
2. Planning & Design | 16 | 16 | 100% | 0 | 0 | 0 | 2026-10-26 | 2026-12-27 | PASSED
3. Build & Configure | 17 | 17 | 100% | 0 | 0 | 0 | 2026-12-28 | 2027-04-04 | PASSED
4. Site Readiness | 9 | 9 | 100% | 0 | 0 | 0 | 2027-03-22 | 2027-06-06 | PASSED
5. Integration & Testing | 9 | 9 | 100% | 0 | 0 | 0 | 2027-04-05 | 2027-07-11 | PASSED
6. Training & Change | 7 | 7 | 100% | 0 | 0 | 0 | 2027-05-03 | 2027-07-25 | PASSED
7. Cutover & Go-Live | 9 | 9 | 100% | 0 | 0 | 0 | 2027-06-28 | 2027-08-15 | PASSED
8. Hypercare & Close | 7 | 0 | 0% | 0 | 0 | 0 | 2027-08-09 | 2027-10-03 | OPEN — 7 item(s)
Total | 81 | 74 | 91.36% | 0 | 0 | 0
Workload by workstream
Workstream | Tasks | Complete | % Complete | In Progress | At Risk / Blocked | Overdue
Automation (MHE) | 6 | 5 | 83.33% | 0 | 0 | 0
Change & Training | 5 | 0 | 0% | 0 | 0 | 0
Cutover & Go-Live | 4 | 0 | 0% | 0 | 0 | 0
Finance | 3 | 2 | 66.67% | 0 | 0 | 0
Hypercare & Close | 3 | 0 | 0% | 0 | 0 | 0
Infrastructure | 3 | 0 | 0% | 0 | 0 | 0
Integration & Data | 9 | 0 | 0% | 0 | 0 | 0
Operations & Staffing | 8 | 0 | 0% | 0 | 0 | 0
PMO | 16 | 10 | 62.5% | 2 | 0 | 0
Safety & Compliance | 2 | 0 | 0% | 0 | 0 | 0
Site Readiness | 4 | 0 | 0% | 0 | 0 | 0
Sponsor | 0 | 0 | 0% | 0 | 0 | 0
Testing | 5 | 0 | 0% | 0 | 0 | 0
Transportation | 4 | 0 | 0% | 0 | 0 | 0
Vendors | 3 | 0 | 0% | 1 | 0 | 0
WMS / WCS | 6 | 6 | 100% | 0 | 0 | 0
Stakeholder assignments (Responsible)
Stakeholder | Responsible for | Accountable for | Open (R) | Overdue (R) | Open RAID owned | Open actions owned
Executive Sponsor | 1 | 15 | 0 | 0 | 0 | 0
Program Manager | 14 | 7 | 11 | 0 | 0 | 0
PMO Analyst | 1 | 0 | 1 | 0 | 0 | 0
Site / Facilities Lead | 5 | 4 | 5 | 0 | 1 | 0
WMS Product Owner | 1 | 7 | 1 | 0 | 0 | 0
WMS Tech Lead | 5 | 1 | 5 | 0 | 0 | 0
WCS / Automation Lead | 2 | 7 | 2 | 0 | 1 | 0
Integration / ERP Lead | 4 | 8 | 4 | 0 | 1 | 0
Data Migration Lead | 5 | 1 | 5 | 0 | 0 | 0
QA / Test Manager | 4 | 2 | 4 | 0 | 1 | 0
Operations Lead | 10 | 11 | 10 | 0 | 1 | 0
Transportation Lead | 4 | 4 | 4 | 0 | 1 | 0
Procurement / Vendor Lead | 3 | 1 | 3 | 0 | 0 | 1
MHE Vendor PM | 4 | 0 | 4 | 0 | 0 | 0
Safety & Compliance Lead | 1 | 2 | 1 | 0 | 0 | 0
Finance Partner | 3 | 2 | 2 | 0 | 0 | 0
Change & Training Lead | 5 | 2 | 5 | 0 | 0 | 0
IT Infrastructure Lead | 3 | 4 | 3 | 0 | 1 | 1
Cutover Manager | 4 | 1 | 4 | 0 | 0 | 0
Hypercare Lead | 2 | 2 | 2 | 0 | 0 | 0
Formulas:
Open RAID items = IF([Total tasks]=0,"",SUMPRODUCT(MIN(('Master Plan'!B5:B185=[Phase])*'Master Plan'!K5:K185+('Master Plan'!B5:B185<>[Phase])*99999)))
High-severity RAID = IF([Total tasks]=0,"",SUMPRODUCT(MAX(('Master Plan'!B5:B185=[Phase])*'Master Plan'!L5:L185)))

## Stakeholders
Stakeholder Register
Blue cells are inputs. Add or rename stakeholders here — dropdowns on every other sheet update automatically.
Stakeholder ID | Role (used in dropdowns) | Name / Title | Organisation | Workstream | Responsibilities | Email | Escalation Contact
SH-01 | Executive Sponsor | VP Supply Chain Operations | Leadership | Sponsor | Approves charter, budget, phase gates and go-live decision | sponsor@company.com | COO
SH-02 | Program Manager | Senior Manager, PMO | PMO | PMO | Owns the playbook, integrated plan, RAID log and gates
SH-03 | PMO Analyst | Project Coordinator | PMO | PMO | Maintains tracker, status reports, action log; runs AI Copilot outputs
SH-04 | Site / Facilities Lead | Director, DC Engineering | Facilities | Site Readiness | Building, utilities, racking, dock doors, permits
SH-05 | WMS Product Owner | Senior Manager, WMS | IT | WMS / WCS | WMS configuration, design decisions, backlog
SH-06 | WMS Tech Lead | Staff Engineer, WMS | IT | WMS / WCS | WMS build, interfaces, environments, code cutover
SH-07 | WCS / Automation Lead | Manager, Automation Engineering | Engineering | Automation (MHE) | Conveyor, sortation, robotics, WCS commissioning
SH-08 | Integration / ERP Lead | Manager, Enterprise Integration | IT | Integration & Data | ERP, OMS, TMS, EDI interfaces and middleware
SH-09 | Data Migration Lead | Senior Data Engineer | IT | Integration & Data | Item master, locations, inventory, customer and vendor data loads
SH-10 | QA / Test Manager | Manager, Quality Engineering | IT | Testing | Test strategy, SIT, UAT, performance test, defect triage
SH-11 | Operations Lead | General Manager, DC | Operations | Operations & Staffing | Process design, SOPs, hiring, shift model, go-live operations
SH-12 | Transportation Lead | Manager, Transportation | Transportation | Transportation | Carrier setup, yard, dock scheduling, TMS routing
SH-13 | Procurement / Vendor Lead | Senior Buyer, Indirect Procurement | Procurement | Vendors | MHE, WMS and construction vendor contracts, SOWs, milestones
SH-14 | MHE Vendor PM | Project Manager (vendor) | External | Automation (MHE) | Vendor delivery of equipment, install, commissioning
SH-15 | Safety & Compliance Lead | Manager, EHS | Safety | Safety & Compliance | OSHA / fire / equipment safety sign-offs, certifications
SH-16 | Finance Partner | Finance Manager, Supply Chain | Finance | Finance | Budget, capex tracking, PO approvals, benefits tracking
SH-17 | Change & Training Lead | Manager, Learning & Change | HR | Change & Training | Training plan, super-users, communications, adoption
SH-18 | IT Infrastructure Lead | Manager, Site Infrastructure | IT | Infrastructure | Network, Wi-Fi, RF devices, printers, servers, cybersecurity
SH-19 | Cutover Manager | Senior Project Manager | PMO | Cutover & Go-Live | Cutover runbook, command center, go / no-go readiness
SH-20 | Hypercare Lead | Support Manager, WMS | IT | Hypercare & Close | Post go-live support, defect resolution, stabilisation metrics

## Objectives
Charter Objectives & Success Criteria (traceability anchor)
Every deliverable and task in the Master Plan traces back to one of these objectives via the Objective ID column.
Objective ID | Objective | Success Criteria / Measure | Accountable (ID) | Tasks Linked | Tasks Complete | % Complete | Status
OBJ-01 | Open the greenfield DC on schedule with production go-live by the committed date | Go-live date achieved; cutover completed within the planned window | SH-01 | 15 | 4 | 26.67% | On Track
OBJ-02 | Deliver a fully operational WMS / WCS stack with no Severity-1 defects at go-live | Zero open Sev-1 defects at go / no-go; SIT and UAT exit criteria met | SH-05 | 20 | 10 | 50% | On Track
OBJ-03 | Commission automation (conveyor, sortation, robotics) at design throughput | Throughput acceptance test passed at ≥ 95% of design rate | SH-07 | 9 | 0 | 0% | On Track
OBJ-04 | Stand up a trained, certified workforce and shift model before first receipt | 100% of go-live associates trained and certified; supervisors signed off | SH-11 | 11 | 5 | 45.45% | On Track
OBJ-05 | Achieve site, safety and regulatory readiness | Certificate of occupancy, fire, OSHA and equipment safety sign-offs complete | SH-15 | 7 | 0 | 0% | On Track
OBJ-06 | Connect inbound and outbound network flows (suppliers, carriers, ERP, TMS) | EDI partners live; carriers onboarded; first inbound and outbound shipments executed | SH-12 | 11 | 0 | 0% | On Track
OBJ-07 | Deliver within approved capex and opex budget | Actual spend within ±5% of approved budget at close | SH-16 | 4 | 3 | 75% | On Track
OBJ-08 | Stabilise operations and hand over to run organisation | Hypercare exit criteria met; lessons learned published; templates updated | SH-20 | 4 | 2 | 50% | On Track

## Master Plan
Master Plan & Traceability Matrix — Greenfield Supply Chain Go-Live
One row per task. Blue = input. Grey = formula (do not edit). Owners are Stakeholder IDs; R/A/C/I trace every stakeholder to every task. Status drives Dashboard, Objectives and Gates.
Task ID | Phase | Workstream | Objective ID | Deliverable | Task / Activity | Responsible (ID) | Accountable (ID) | Consulted (ID) | Informed (ID) | Start | Due | Duration (days) | Status | % Complete | Predecessors | AI Copilot Moment | Gate | Evidence / Link | Days Overdue | Health | Last Updated | Notes
T-001 | 1. Initiation | PMO | OBJ-01 | Project Charter | Draft charter from business case using AI Copilot (scope, objectives, success metrics, constraints) | SH-02 | SH-01 | SH-16 | SH-11 | 2026-10-05 | 2026-10-11 | 7 | Complete | 100% |  | Intake | G1 |  | 0 | Done | 2026-10-26
T-002 | 1. Initiation | PMO | OBJ-01 | Project Charter | Review and approve charter | SH-01 | SH-01 | SH-02 | SH-03 | 2026-10-12 | 2026-10-18 | 7 | Complete | 100% | T-001 | Intake | G1 |  | 0 | Done | 2026-10-26
T-003 | 1. Initiation | PMO | OBJ-01 | Stakeholder Register | Identify stakeholders, confirm roles and escalation paths | SH-02 | SH-01 | SH-11 | SH-03 | 2026-10-05 | 2026-10-11 | 7 | Complete | 100% |  | Intake | G1 |  | 0 | Done | 2026-10-26
T-004 | 1. Initiation | Finance | OBJ-07 | Budget Baseline | Approve capex / opex baseline and funding release | SH-16 | SH-01 | SH-02 | SH-13 | 2026-10-12 | 2026-10-25 | 14 | Complete | 100% | T-002 | Intake | G1 |  | 0 | Done | 2026-10-26
T-005 | 1. Initiation | PMO | OBJ-01 | Governance Model | Set up steering committee cadence, RAID log and Completeness Gate checklists | SH-02 | SH-01 | SH-03 | SH-11 | 2026-10-12 | 2026-10-18 | 7 | Complete | 100% | T-002 | Plan | G1 |  | 0 | Done | 2026-10-26
T-006 | 1. Initiation | Vendors | OBJ-03 | Vendor Shortlist | Confirm MHE, WMS and construction vendors and SOW status | SH-13 | SH-02 | SH-07 | SH-16 | 2026-10-12 | 2026-10-25 | 14 | In Progress | 40% |  | Intake | G1 |  | 0 | Green | 2026-10-26
T-007 | 1. Initiation | PMO | OBJ-01 | Gate 1 Review | Completeness Gate 1: charter, budget, stakeholders, governance approved | SH-02 | SH-01 | SH-03 | SH-11 | 2026-10-26 | 2026-11-01 | 7 | In Progress | 40% | T-002,T-004,T-005 | Communicate | G1 |  | 0 | Green | 2026-10-26
T-008 | 2. Planning & Design | PMO | OBJ-01 | Integrated Master Plan | Generate WBS from greenfield template; confirm dependencies and critical path | SH-02 | SH-01 | SH-05 | SH-11 | 2026-10-26 | 2026-11-08 | 14 | In Progress | 40% | T-007 | Plan | G2 |  | 0 | Green | 2026-10-26
T-009 | 2. Planning & Design | PMO | OBJ-01 | RAID Baseline | Create RAID baseline with owners and due dates | SH-02 | SH-02 | SH-05 | SH-01 | 2026-10-26 | 2026-11-01 | 7 | Not Started | 0% | T-007 | Plan | G2 |  | 0 | Green | 2026-10-26
T-010 | 2. Planning & Design | Site Readiness | OBJ-05 | Facility Design | Finalise building layout, racking, dock doors and utilities design | SH-04 | SH-04 | SH-07 | SH-11 | 2026-10-26 | 2026-11-22 | 28 | Not Started | 0% | T-008 | Plan | G2 |  | 0 | Green
T-011 | 2. Planning & Design | Site Readiness | OBJ-05 | Permits | Submit building, fire and occupancy permit applications | SH-04 | SH-04 | SH-15 | SH-02 | 2026-11-09 | 2026-11-29 | 21 | Not Started | 0% | T-010 | Monitor | G2 |  | 0 | Green
T-012 | 2. Planning & Design | Operations & Staffing | OBJ-04 | Process Design | Design inbound, putaway, pick, pack, ship and returns processes (to-be) | SH-11 | SH-11 | SH-05 | SH-17 | 2026-11-02 | 2026-11-29 | 28 | Not Started | 0% | T-008 | Plan | G2 |  | 0 | Green
T-013 | 2. Planning & Design | WMS / WCS | OBJ-02 | WMS Functional Design | Fit-gap workshops and functional design document sign-off | SH-05 | SH-05 | SH-11 | SH-06 | 2026-11-09 | 2026-12-06 | 28 | Not Started | 0% | T-012 | Plan | G2 |  | 0 | Green
T-014 | 2. Planning & Design | WMS / WCS | OBJ-02 | WMS Technical Design | Technical design: environments, interfaces, data model, security | SH-06 | SH-05 | SH-08 | SH-18 | 2026-11-16 | 2026-12-06 | 21 | Not Started | 0% | T-013 | Plan | G2 |  | 0 | Green
T-015 | 2. Planning & Design | Automation (MHE) | OBJ-03 | Automation Design | Approve MHE layout, throughput model and WCS control philosophy | SH-07 | SH-07 | SH-14 | SH-05 | 2026-11-02 | 2026-12-06 | 35 | Not Started | 0% | T-010 | Plan | G2 |  | 0 | Green
T-016 | 2. Planning & Design | Integration & Data | OBJ-06 | Interface Catalogue | Define all ERP / OMS / TMS / WCS / EDI interfaces with owners | SH-08 | SH-08 | SH-06 | SH-12 | 2026-11-16 | 2026-12-06 | 21 | Not Started | 0% | T-014 | Plan | G2 |  | 0 | Green
T-017 | 2. Planning & Design | Integration & Data | OBJ-02 | Data Migration Strategy | Define data objects, sources, cleansing rules and load sequence | SH-09 | SH-08 | SH-05 | SH-11 | 2026-11-23 | 2026-12-06 | 14 | Not Started | 0% | T-016 | Plan | G2 |  | 0 | Green
T-018 | 2. Planning & Design | Testing | OBJ-02 | Test Strategy | Approve test strategy: unit, SIT, UAT, performance, throughput acceptance | SH-10 | SH-10 | SH-05 | SH-07 | 2026-11-30 | 2026-12-13 | 14 | Not Started | 0% | T-013 | Plan | G2 |  | 0 | Green
T-019 | 2. Planning & Design | Infrastructure | OBJ-02 | Infrastructure Design | Design network, Wi-Fi survey, RF devices, printers, server / cloud | SH-18 | SH-18 | SH-06 | SH-04 | 2026-11-16 | 2026-12-06 | 21 | Not Started | 0% | T-010 | Plan | G2 |  | 0 | Green
T-020 | 2. Planning & Design | Transportation | OBJ-06 | Transportation Design | Design carrier network, yard and dock scheduling, TMS routing | SH-12 | SH-12 | SH-11 | SH-08 | 2026-11-23 | 2026-12-13 | 21 | Not Started | 0% | T-012 | Plan | G2 |  | 0 | Green
T-021 | 2. Planning & Design | Change & Training | OBJ-04 | Change Plan | Change impact assessment, communication and training plan | SH-17 | SH-17 | SH-11 | SH-02 | 2026-11-30 | 2026-12-13 | 14 | Not Started | 0% | T-012 | Plan | G2 |  | 0 | Green
T-022 | 2. Planning & Design | Vendors | OBJ-07 | Vendor Contracts | Execute MHE, WMS and construction contracts with milestone schedule | SH-13 | SH-13 | SH-16 | SH-02 | 2026-11-02 | 2026-11-29 | 28 | Not Started | 0% | T-006 | Monitor | G2 |  | 0 | Green
T-023 | 2. Planning & Design | PMO | OBJ-01 | Gate 2 Review | Completeness Gate 2: all designs, plan, RAID and contracts approved | SH-02 | SH-01 | SH-05 | SH-11 | 2026-12-21 | 2026-12-27 | 7 | Not Started | 0% | T-013,T-015,T-016,T-022 | Communicate | G2 |  | 0 | Green
T-024 | 3. Build & Configure | WMS / WCS | OBJ-02 | WMS Configuration | Configure WMS: locations, zones, rules, workflows, labels | SH-06 | SH-05 | SH-11 | SH-10 | 2026-12-28 | 2027-02-21 | 56 | Not Started | 0% | T-023 | Monitor | G3 |  | 0 | Green
T-025 | 3. Build & Configure | WMS / WCS | OBJ-02 | WMS Custom Development | Build approved customisations and reports | SH-06 | SH-05 | SH-10 | SH-02 | 2027-01-11 | 2027-03-07 | 56 | Not Started | 0% | T-024 | Monitor | G3 |  | 0 | Green
T-026 | 3. Build & Configure | WMS / WCS | OBJ-02 | Environment Build | Provision DEV / TEST / PROD environments and CI/CD | SH-06 | SH-18 | SH-08 | SH-10 | 2026-12-28 | 2027-01-17 | 21 | Not Started | 0% | T-023 | Monitor | G3 |  | 0 | Green
T-027 | 3. Build & Configure | Integration & Data | OBJ-06 | Interface Development | Develop and unit test all interfaces per catalogue | SH-08 | SH-08 | SH-06 | SH-12 | 2027-01-11 | 2027-03-21 | 70 | Not Started | 0% | T-026 | Monitor | G3 |  | 0 | Green
T-028 | 3. Build & Configure | Integration & Data | OBJ-06 | EDI Partner Setup | Set up EDI with priority suppliers and carriers | SH-08 | SH-08 | SH-13 | SH-12 | 2027-02-08 | 2027-03-21 | 42 | Not Started | 0% | T-027 | Monitor | G3 |  | 0 | Green
T-029 | 3. Build & Configure | Integration & Data | OBJ-02 | Data Cleansing | Cleanse item master, vendor, customer and location data | SH-09 | SH-09 | SH-11 | SH-05 | 2027-01-11 | 2027-03-07 | 56 | Not Started | 0% | T-017 | Monitor | G3 |  | 0 | Green
T-030 | 3. Build & Configure | Integration & Data | OBJ-02 | Mock Data Load 1 | Execute first mock migration into TEST | SH-09 | SH-08 | SH-06 | SH-10 | 2027-03-08 | 2027-03-21 | 14 | Not Started | 0% | T-029,T-026 | Monitor | G3 |  | 0 | Green
T-031 | 3. Build & Configure | Automation (MHE) | OBJ-03 | Equipment Manufacture | Vendor manufactures conveyor, sortation and robotics | SH-14 | SH-07 | SH-13 | SH-02 | 2026-12-28 | 2027-03-21 | 84 | Not Started | 0% | T-022 | Monitor | G3 |  | 0 | Green
T-032 | 3. Build & Configure | Automation (MHE) | OBJ-03 | WCS Development | Vendor develops WCS and emulation model | SH-14 | SH-07 | SH-06 | SH-10 | 2027-01-11 | 2027-03-21 | 70 | Not Started | 0% | T-015 | Monitor | G3 |  | 0 | Green
T-033 | 3. Build & Configure | Site Readiness | OBJ-05 | Construction | Building shell, floor, utilities and fire suppression complete | SH-04 | SH-04 | SH-15 | SH-07 | 2026-12-28 | 2027-04-04 | 98 | Not Started | 0% | T-011 | Monitor | G3 |  | 0 | Green
T-034 | 3. Build & Configure | Infrastructure | OBJ-02 | Network & RF Install | Install network, Wi-Fi, RF devices and printers | SH-18 | SH-18 | SH-04 | SH-06 | 2027-03-08 | 2027-04-04 | 28 | Not Started | 0% | T-033,T-019 | Monitor | G3 |  | 0 | Green
T-035 | 3. Build & Configure | Operations & Staffing | OBJ-04 | SOP Development | Write SOPs and work instructions for every process | SH-11 | SH-11 | SH-17 | SH-05 | 2027-01-25 | 2027-03-21 | 56 | Not Started | 0% | T-012 | Monitor | G3 |  | 0 | Green
T-036 | 3. Build & Configure | Operations & Staffing | OBJ-04 | Hiring Plan | Approve hiring plan, shift model and recruiting start | SH-11 | SH-11 | SH-17 | SH-16 | 2027-01-25 | 2027-02-21 | 28 | Not Started | 0% | T-012 | Monitor | G3 |  | 0 | Green
T-037 | 3. Build & Configure | Transportation | OBJ-06 | Carrier Onboarding | Contract and onboard carriers; configure TMS lanes | SH-12 | SH-12 | SH-08 | SH-13 | 2027-02-08 | 2027-03-21 | 42 | Not Started | 0% | T-020 | Monitor | G3 |  | 0 | Green
T-038 | 3. Build & Configure | Finance | OBJ-07 | Capex Tracking | Monthly capex vs. budget review with variance explanations | SH-16 | SH-16 | SH-02 | SH-01 | 2026-12-28 | 2027-04-04 | 98 | Not Started | 0% | T-004 | Communicate | G3 |  | 0 | Green
T-039 | 3. Build & Configure | PMO | OBJ-01 | Weekly Status Report | AI-drafted weekly status and exception review (recurring through go-live) | SH-03 | SH-02 | SH-05 | SH-01 | 2026-12-28 | 2027-04-04 | 98 | Not Started | 0% | T-007 | Communicate |  |  | 0 | Green
T-040 | 3. Build & Configure | PMO | OBJ-01 | Gate 3 Review | Completeness Gate 3: build complete, construction and equipment on schedule | SH-02 | SH-01 | SH-06 | SH-07 | 2027-03-29 | 2027-04-04 | 7 | Not Started | 0% | T-024,T-025,T-027,T-033 | Communicate | G3 |  | 0 | Green
T-041 | 4. Site Readiness | Site Readiness | OBJ-05 | Racking Install | Install racking, mezzanine and dock equipment | SH-04 | SH-04 | SH-15 | SH-11 | 2027-03-22 | 2027-04-25 | 35 | Not Started | 0% | T-033 | Monitor | G4 |  | 0 | Green
T-042 | 4. Site Readiness | Automation (MHE) | OBJ-03 | MHE Installation | Mechanical and electrical installation of automation | SH-14 | SH-07 | SH-04 | SH-15 | 2027-04-05 | 2027-05-16 | 42 | Not Started | 0% | T-031,T-033 | Monitor | G4 |  | 0 | Green
T-043 | 4. Site Readiness | Automation (MHE) | OBJ-03 | MHE Commissioning | Dry commissioning and WCS control testing | SH-14 | SH-07 | SH-06 | SH-10 | 2027-05-10 | 2027-05-30 | 21 | Not Started | 0% | T-042,T-032 | Monitor | G4 |  | 0 | Green
T-044 | 4. Site Readiness | Safety & Compliance | OBJ-05 | Safety Inspections | Fire marshal, OSHA and equipment safety inspections | SH-15 | SH-15 | SH-04 | SH-02 | 2027-05-03 | 2027-05-23 | 21 | Not Started | 0% | T-041,T-042 | Monitor | G4 |  | 0 | Green
T-045 | 4. Site Readiness | Safety & Compliance | OBJ-05 | Certificate of Occupancy | Obtain certificate of occupancy | SH-04 | SH-15 | SH-02 | SH-01 | 2027-05-17 | 2027-05-30 | 14 | Not Started | 0% | T-044 | Monitor | G4 |  | 0 | Green
T-046 | 4. Site Readiness | Operations & Staffing | OBJ-04 | Supervisor Hiring | Hire and onboard supervisors and leads | SH-11 | SH-11 | SH-17 | SH-02 | 2027-03-22 | 2027-05-02 | 42 | Not Started | 0% | T-036 | Monitor | G4 |  | 0 | Green
T-047 | 4. Site Readiness | Infrastructure | OBJ-02 | Site IT Go-Live | Site network, RF and printers live and tested | SH-18 | SH-18 | SH-06 | SH-11 | 2027-04-19 | 2027-05-02 | 14 | Not Started | 0% | T-034 | Monitor | G4 |  | 0 | Green
T-048 | 4. Site Readiness | Transportation | OBJ-06 | Yard & Dock Setup | Yard management, dock scheduling and gate procedures ready | SH-12 | SH-12 | SH-11 | SH-04 | 2027-05-03 | 2027-05-23 | 21 | Not Started | 0% | T-037,T-041 | Monitor | G4 |  | 0 | Green
T-049 | 4. Site Readiness | PMO | OBJ-05 | Gate 4 Review | Completeness Gate 4: site, safety, equipment and infrastructure ready | SH-02 | SH-01 | SH-04 | SH-15 | 2027-05-31 | 2027-06-06 | 7 | Not Started | 0% | T-043,T-045,T-047 | Communicate | G4 |  | 0 | Green
T-050 | 5. Integration & Testing | Testing | OBJ-02 | System Integration Test | SIT cycles 1-2 across WMS, ERP, OMS, TMS and WCS emulation | SH-10 | SH-10 | SH-06 | SH-05 | 2027-04-05 | 2027-05-16 | 42 | Not Started | 0% | T-027,T-030 | Monitor | G5 |  | 0 | Green
T-051 | 5. Integration & Testing | Testing | OBJ-02 | Defect Management | Daily defect triage; Sev-1 / Sev-2 burn-down tracked | SH-10 | SH-05 | SH-06 | SH-02 | 2027-04-05 | 2027-07-11 | 98 | Not Started | 0% | T-050 | Monitor |  |  | 0 | Green
T-052 | 5. Integration & Testing | Integration & Data | OBJ-02 | Mock Data Load 2 | Full-volume mock migration with reconciliation report | SH-09 | SH-08 | SH-06 | SH-10 | 2027-05-17 | 2027-05-30 | 14 | Not Started | 0% | T-030 | Monitor | G5 |  | 0 | Green
T-053 | 5. Integration & Testing | Testing | OBJ-02 | Performance Test | Peak-volume performance and interface load test | SH-10 | SH-06 | SH-08 | SH-18 | 2027-05-24 | 2027-06-06 | 14 | Not Started | 0% | T-050,T-052 | Monitor | G5 |  | 0 | Green
T-054 | 5. Integration & Testing | Automation (MHE) | OBJ-03 | Throughput Acceptance Test | Integrated WMS / WCS / MHE throughput test at design rate | SH-07 | SH-07 | SH-14 | SH-11 | 2027-05-31 | 2027-06-20 | 21 | Not Started | 0% | T-043,T-050 | Monitor | G5 |  | 0 | Green
T-055 | 5. Integration & Testing | Testing | OBJ-02 | User Acceptance Test | UAT with operations super-users; exit criteria signed | SH-11 | SH-05 | SH-10 | SH-17 | 2027-06-07 | 2027-07-04 | 28 | Not Started | 0% | T-050,T-035 | Monitor | G5 |  | 0 | Green
T-056 | 5. Integration & Testing | Transportation | OBJ-06 | Carrier Connectivity Test | End-to-end label, manifest and EDI 214/210 test with carriers | SH-12 | SH-12 | SH-08 | SH-10 | 2027-06-14 | 2027-06-27 | 14 | Not Started | 0% | T-037,T-028 | Monitor | G5 |  | 0 | Green
T-057 | 5. Integration & Testing | Integration & Data | OBJ-06 | Supplier EDI Test | Test ASN / PO / invoice with priority suppliers | SH-08 | SH-08 | SH-13 | SH-11 | 2027-06-14 | 2027-06-27 | 14 | Not Started | 0% | T-028 | Monitor | G5 |  | 0 | Green
T-058 | 5. Integration & Testing | PMO | OBJ-02 | Gate 5 Review | Completeness Gate 5: SIT / UAT / performance / throughput exit criteria met, no open Sev-1 | SH-02 | SH-01 | SH-10 | SH-05 | 2027-07-05 | 2027-07-11 | 7 | Not Started | 0% | T-053,T-054,T-055 | Communicate | G5 |  | 0 | Green
T-059 | 6. Training & Change | Change & Training | OBJ-04 | Training Content | Build role-based training and job aids from SOPs | SH-17 | SH-17 | SH-11 | SH-05 | 2027-05-03 | 2027-06-06 | 35 | Not Started | 0% | T-035 | Monitor | G6 |  | 0 | Green
T-060 | 6. Training & Change | Change & Training | OBJ-04 | Super-User Training | Train and certify super-users (one per process area per shift) | SH-17 | SH-11 | SH-05 | SH-10 | 2027-05-31 | 2027-06-13 | 14 | Not Started | 0% | T-059,T-046 | Monitor | G6 |  | 0 | Green
T-061 | 6. Training & Change | Operations & Staffing | OBJ-04 | Associate Hiring | Hire go-live associate headcount | SH-11 | SH-11 | SH-17 | SH-16 | 2027-05-03 | 2027-06-27 | 56 | Not Started | 0% | T-036 | Monitor | G6 |  | 0 | Green
T-062 | 6. Training & Change | Change & Training | OBJ-04 | Associate Training | Train and certify all go-live associates (hands-on in TEST) | SH-17 | SH-11 | SH-05 | SH-15 | 2027-06-28 | 2027-07-18 | 21 | Not Started | 0% | T-060,T-061 | Monitor | G6 |  | 0 | Green
T-063 | 6. Training & Change | Change & Training | OBJ-06 | Communications | Stakeholder and customer / supplier go-live communications | SH-17 | SH-02 | SH-12 | SH-13 | 2027-06-14 | 2027-07-18 | 35 | Not Started | 0% | T-021 | Communicate |  |  | 0 | Green
T-064 | 6. Training & Change | Operations & Staffing | OBJ-04 | Operational Dress Rehearsal | Simulated day-in-the-life with real equipment and system | SH-11 | SH-11 | SH-07 | SH-05 | 2027-07-12 | 2027-07-18 | 7 | Not Started | 0% | T-062,T-054 | Monitor | G6 |  | 0 | Green
T-065 | 6. Training & Change | PMO | OBJ-04 | Gate 6 Review | Completeness Gate 6: 100% training certified, rehearsal passed | SH-02 | SH-01 | SH-17 | SH-11 | 2027-07-19 | 2027-07-25 | 7 | Not Started | 0% | T-062,T-064 | Communicate | G6 |  | 0 | Green
T-066 | 7. Cutover & Go-Live | Cutover & Go-Live | OBJ-01 | Cutover Runbook | Minute-by-minute cutover runbook with owners and rollback plan | SH-19 | SH-02 | SH-06 | SH-11 | 2027-06-28 | 2027-07-11 | 14 | Not Started | 0% | T-058 | Plan | G7 |  | 0 | Green
T-067 | 7. Cutover & Go-Live | Cutover & Go-Live | OBJ-01 | Cutover Rehearsal | Full cutover rehearsal in TEST including data load timing | SH-19 | SH-19 | SH-09 | SH-08 | 2027-07-12 | 2027-07-18 | 7 | Not Started | 0% | T-066,T-052 | Monitor | G7 |  | 0 | Green
T-068 | 7. Cutover & Go-Live | Cutover & Go-Live | OBJ-01 | Go / No-Go Readiness | Readiness assessment across all workstreams; sponsor decision | SH-19 | SH-01 | SH-02 | SH-11 | 2027-07-26 | 2027-08-01 | 7 | Not Started | 0% | T-058,T-065,T-067 | Communicate | G7 |  | 0 | Green
T-069 | 7. Cutover & Go-Live | Integration & Data | OBJ-02 | Production Data Load | Final data migration into PROD with reconciliation sign-off | SH-09 | SH-08 | SH-06 | SH-11 | 2027-08-02 | 2027-08-08 | 7 | Not Started | 0% | T-068 | Monitor | G7 |  | 0 | Green
T-070 | 7. Cutover & Go-Live | WMS / WCS | OBJ-02 | Production Code Deploy | Deploy WMS / interfaces to PROD; smoke test | SH-06 | SH-05 | SH-18 | SH-19 | 2027-08-02 | 2027-08-08 | 7 | Not Started | 0% | T-068 | Monitor | G7 |  | 0 | Green
T-071 | 7. Cutover & Go-Live | Cutover & Go-Live | OBJ-01 | Command Center | Stand up go-live command center and escalation rota | SH-19 | SH-02 | SH-20 | SH-11 | 2027-08-02 | 2027-08-15 | 14 | Not Started | 0% | T-068 | Communicate |  |  | 0 | Green
T-072 | 7. Cutover & Go-Live | Operations & Staffing | OBJ-06 | First Inbound Receipt | Execute first inbound receipt and putaway in production | SH-11 | SH-11 | SH-12 | SH-05 | 2027-08-09 | 2027-08-15 | 7 | Not Started | 0% | T-069,T-070 | Monitor | G7 |  | 0 | Green
T-073 | 7. Cutover & Go-Live | Operations & Staffing | OBJ-06 | First Outbound Shipment | Execute first pick, pack, ship and carrier tender | SH-11 | SH-11 | SH-12 | SH-05 | 2027-08-09 | 2027-08-15 | 7 | Not Started | 0% | T-072 | Monitor | G7 |  | 0 | Green
T-074 | 7. Cutover & Go-Live | PMO | OBJ-01 | Gate 7 Review | Completeness Gate 7: production go-live achieved, first shipments confirmed | SH-02 | SH-01 | SH-19 | SH-11 | 2027-08-09 | 2027-08-15 | 7 | Not Started | 0% | T-072,T-073 | Communicate | G7 |  | 0 | Green
T-075 | 8. Hypercare & Close | Hypercare & Close | OBJ-08 | Hypercare Support | Daily stabilisation review: defects, throughput, inventory accuracy | SH-20 | SH-20 | SH-11 | SH-05 | 2027-08-09 | 2027-09-19 | 42 | Not Started | 0% | T-074 | Monitor |  |  | 0 | Green
T-076 | 8. Hypercare & Close | Hypercare & Close | OBJ-03 | Volume Ramp | Ramp to planned volume against ramp curve | SH-11 | SH-11 | SH-07 | SH-12 | 2027-08-16 | 2027-09-26 | 42 | Not Started | 0% | T-074 | Monitor | G8 |  | 0 | Green
T-077 | 8. Hypercare & Close | Finance | OBJ-07 | Financial Close | Final capex reconciliation and benefits baseline | SH-16 | SH-16 | SH-02 | SH-01 | 2027-09-06 | 2027-09-26 | 21 | Not Started | 0% | T-038 | Close | G8 |  | 0 | Green
T-078 | 8. Hypercare & Close | Vendors | OBJ-03 | Vendor Acceptance | Final acceptance certificates and warranty start for MHE / WMS | SH-13 | SH-07 | SH-14 | SH-16 | 2027-09-06 | 2027-09-19 | 14 | Not Started | 0% | T-054 | Close | G8 |  | 0 | Green
T-079 | 8. Hypercare & Close | Hypercare & Close | OBJ-08 | Handover to Run | Transition to run support; knowledge transfer complete | SH-20 | SH-20 | SH-06 | SH-11 | 2027-09-20 | 2027-09-26 | 7 | Not Started | 0% | T-075 | Close | G8 |  | 0 | Green
T-080 | 8. Hypercare & Close | PMO | OBJ-08 | Lessons Learned | AI-summarised lessons learned from RAID log and status history; templates updated | SH-02 | SH-02 | SH-11 | SH-01 | 2027-09-20 | 2027-09-26 | 7 | Not Started | 0% | T-075 | Close | G8 |  | 0 | Green
T-081 | 8. Hypercare & Close | PMO | OBJ-08 | Gate 8 Review | Completeness Gate 8: hypercare exit, financial close, lessons published, project archived | SH-02 | SH-01 | SH-20 | SH-16 | 2027-09-27 | 2027-10-03 | 7 | Not Started | 0% | T-076,T-077,T-079,T-080 | Close | G8 |  | 0 | Green
Formulas:
Days Overdue = IF(OR([Status]="Complete",[Status]="Deferred",[Due]=""),0,MAX(0,TODAY()-[Due]))
Health = IF([Status]="Complete","Done",IF(OR([Status]="Blocked",[Days Overdue]>5),"Red",IF(OR([Status]="At Risk",[Days Overdue]>0,AND([Status]="Not Started",[Start]<TODAY())),"Amber","Green")))
Note on T4: Days past Due while not Complete/Deferred. Uses TODAY().
Note on U4: Red: Blocked or >5 days overdue. Amber: At Risk, any overdue, or Not Started past Start date. Green: otherwise. Done: Complete.

## RACI Matrix
RACI Traceability Matrix — every stakeholder against every task (auto-derived from Master Plan)
Formula-driven: R = Responsible, A = Accountable, C = Consulted, I = Informed. Edit assignments in Master Plan columns G–J, not here. Totals at right show each stakeholder's load.
|  |  | Stakeholder ID → | SH-01 | SH-02 | SH-03 | SH-04 | SH-05 | SH-06 | SH-07 | SH-08 | SH-09 | SH-10 | SH-11 | SH-12 | SH-13 | SH-14 | SH-15 | SH-16 | SH-17 | SH-18 | SH-19 | SH-20
Task ID | Phase | Deliverable | Status | Executive Sponsor | Program Manager | PMO Analyst | Site / Facilities Lead | WMS Product Owner | WMS Tech Lead | WCS / Automation Lead | Integration / ERP Lead | Data Migration Lead | QA / Test Manager | Operations Lead | Transportation Lead | Procurement / Vendor Lead | MHE Vendor PM | Safety & Compliance Lead | Finance Partner | Change & Training Lead | IT Infrastructure Lead | Cutover Manager | Hypercare Lead | # R | # A | # C | # I
T-001 | 1. Initiation | Project Charter | Complete | SH-01: A; SH-02: R; SH-11: I; SH-16: C | 1 | 1 | 1 | 1
T-002 | 1. Initiation | Project Charter | Complete | SH-01: R; SH-02: C; SH-03: I | 1 | 0 | 1 | 1
T-003 | 1. Initiation | Stakeholder Register | Complete | SH-01: A; SH-02: R; SH-03: I; SH-11: C | 1 | 1 | 1 | 1
T-004 | 1. Initiation | Budget Baseline | Complete | SH-01: A; SH-02: C; SH-13: I; SH-16: R | 1 | 1 | 1 | 1
T-005 | 1. Initiation | Governance Model | Complete | SH-01: A; SH-02: R; SH-03: C; SH-11: I | 1 | 1 | 1 | 1
T-006 | 1. Initiation | Vendor Shortlist | In Progress | SH-02: A; SH-07: C; SH-13: R; SH-16: I | 1 | 1 | 1 | 1
T-007 | 1. Initiation | Gate 1 Review | In Progress | SH-01: A; SH-02: R; SH-03: C; SH-11: I | 1 | 1 | 1 | 1
T-008 | 2. Planning & Design | Integrated Master Plan | In Progress | SH-01: A; SH-02: R; SH-05: C; SH-11: I | 1 | 1 | 1 | 1
T-009 | 2. Planning & Design | RAID Baseline | Not Started | SH-01: I; SH-02: R; SH-05: C | 1 | 0 | 1 | 1
T-010 | 2. Planning & Design | Facility Design | Not Started | SH-04: R; SH-07: C; SH-11: I | 1 | 0 | 1 | 1
T-011 | 2. Planning & Design | Permits | Not Started | SH-02: I; SH-04: R; SH-15: C | 1 | 0 | 1 | 1
T-012 | 2. Planning & Design | Process Design | Not Started | SH-05: C; SH-11: R; SH-17: I | 1 | 0 | 1 | 1
T-013 | 2. Planning & Design | WMS Functional Design | Not Started | SH-05: R; SH-06: I; SH-11: C | 1 | 0 | 1 | 1
T-014 | 2. Planning & Design | WMS Technical Design | Not Started | SH-05: A; SH-06: R; SH-08: C; SH-18: I | 1 | 1 | 1 | 1
T-015 | 2. Planning & Design | Automation Design | Not Started | SH-05: I; SH-07: R; SH-14: C | 1 | 0 | 1 | 1
T-016 | 2. Planning & Design | Interface Catalogue | Not Started | SH-06: C; SH-08: R; SH-12: I | 1 | 0 | 1 | 1
T-017 | 2. Planning & Design | Data Migration Strategy | Not Started | SH-05: C; SH-08: A; SH-09: R; SH-11: I | 1 | 1 | 1 | 1
T-018 | 2. Planning & Design | Test Strategy | Not Started | SH-05: C; SH-07: I; SH-10: R | 1 | 0 | 1 | 1
T-019 | 2. Planning & Design | Infrastructure Design | Not Started | SH-04: I; SH-06: C; SH-18: R | 1 | 0 | 1 | 1
T-020 | 2. Planning & Design | Transportation Design | Not Started | SH-08: I; SH-11: C; SH-12: R | 1 | 0 | 1 | 1
T-021 | 2. Planning & Design | Change Plan | Not Started | SH-02: I; SH-11: C; SH-17: R | 1 | 0 | 1 | 1
T-022 | 2. Planning & Design | Vendor Contracts | Not Started | SH-02: I; SH-13: R; SH-16: C | 1 | 0 | 1 | 1
T-023 | 2. Planning & Design | Gate 2 Review | Not Started | SH-01: A; SH-02: R; SH-05: C; SH-11: I | 1 | 1 | 1 | 1
T-024 | 3. Build & Configure | WMS Configuration | Not Started | SH-05: A; SH-06: R; SH-10: I; SH-11: C | 1 | 1 | 1 | 1
T-025 | 3. Build & Configure | WMS Custom Development | Not Started | SH-02: I; SH-05: A; SH-06: R; SH-10: C | 1 | 1 | 1 | 1
T-026 | 3. Build & Configure | Environment Build | Not Started | SH-06: R; SH-08: C; SH-10: I; SH-18: A | 1 | 1 | 1 | 1
T-027 | 3. Build & Configure | Interface Development | Not Started | SH-06: C; SH-08: R; SH-12: I | 1 | 0 | 1 | 1
T-028 | 3. Build & Configure | EDI Partner Setup | Not Started | SH-08: R; SH-12: I; SH-13: C | 1 | 0 | 1 | 1
T-029 | 3. Build & Configure | Data Cleansing | Not Started | SH-05: I; SH-09: R; SH-11: C | 1 | 0 | 1 | 1
T-030 | 3. Build & Configure | Mock Data Load 1 | Not Started | SH-06: C; SH-08: A; SH-09: R; SH-10: I | 1 | 1 | 1 | 1
T-031 | 3. Build & Configure | Equipment Manufacture | Not Started | SH-02: I; SH-07: A; SH-13: C; SH-14: R | 1 | 1 | 1 | 1
T-032 | 3. Build & Configure | WCS Development | Not Started | SH-06: C; SH-07: A; SH-10: I; SH-14: R | 1 | 1 | 1 | 1
T-033 | 3. Build & Configure | Construction | Not Started | SH-04: R; SH-07: I; SH-15: C | 1 | 0 | 1 | 1
T-034 | 3. Build & Configure | Network & RF Install | Not Started | SH-04: C; SH-06: I; SH-18: R | 1 | 0 | 1 | 1
T-035 | 3. Build & Configure | SOP Development | Not Started | SH-05: I; SH-11: R; SH-17: C | 1 | 0 | 1 | 1
T-036 | 3. Build & Configure | Hiring Plan | Not Started | SH-11: R; SH-16: I; SH-17: C | 1 | 0 | 1 | 1
T-037 | 3. Build & Configure | Carrier Onboarding | Not Started | SH-08: C; SH-12: R; SH-13: I | 1 | 0 | 1 | 1
T-038 | 3. Build & Configure | Capex Tracking | Not Started | SH-01: I; SH-02: C; SH-16: R | 1 | 0 | 1 | 1
T-039 | 3. Build & Configure | Weekly Status Report | Not Started | SH-01: I; SH-02: A; SH-03: R; SH-05: C | 1 | 1 | 1 | 1
T-040 | 3. Build & Configure | Gate 3 Review | Not Started | SH-01: A; SH-02: R; SH-06: C; SH-07: I | 1 | 1 | 1 | 1
T-041 | 4. Site Readiness | Racking Install | Not Started | SH-04: R; SH-11: I; SH-15: C | 1 | 0 | 1 | 1
T-042 | 4. Site Readiness | MHE Installation | Not Started | SH-04: C; SH-07: A; SH-14: R; SH-15: I | 1 | 1 | 1 | 1
T-043 | 4. Site Readiness | MHE Commissioning | Not Started | SH-06: C; SH-07: A; SH-10: I; SH-14: R | 1 | 1 | 1 | 1
T-044 | 4. Site Readiness | Safety Inspections | Not Started | SH-02: I; SH-04: C; SH-15: R | 1 | 0 | 1 | 1
T-045 | 4. Site Readiness | Certificate of Occupancy | Not Started | SH-01: I; SH-02: C; SH-04: R; SH-15: A | 1 | 1 | 1 | 1
T-046 | 4. Site Readiness | Supervisor Hiring | Not Started | SH-02: I; SH-11: R; SH-17: C | 1 | 0 | 1 | 1
T-047 | 4. Site Readiness | Site IT Go-Live | Not Started | SH-06: C; SH-11: I; SH-18: R | 1 | 0 | 1 | 1
T-048 | 4. Site Readiness | Yard & Dock Setup | Not Started | SH-04: I; SH-11: C; SH-12: R | 1 | 0 | 1 | 1
T-049 | 4. Site Readiness | Gate 4 Review | Not Started | SH-01: A; SH-02: R; SH-04: C; SH-15: I | 1 | 1 | 1 | 1
T-050 | 5. Integration & Testing | System Integration Test | Not Started | SH-05: I; SH-06: C; SH-10: R | 1 | 0 | 1 | 1
T-051 | 5. Integration & Testing | Defect Management | Not Started | SH-02: I; SH-05: A; SH-06: C; SH-10: R | 1 | 1 | 1 | 1
T-052 | 5. Integration & Testing | Mock Data Load 2 | Not Started | SH-06: C; SH-08: A; SH-09: R; SH-10: I | 1 | 1 | 1 | 1
T-053 | 5. Integration & Testing | Performance Test | Not Started | SH-06: A; SH-08: C; SH-10: R; SH-18: I | 1 | 1 | 1 | 1
T-054 | 5. Integration & Testing | Throughput Acceptance Test | Not Started | SH-07: R; SH-11: I; SH-14: C | 1 | 0 | 1 | 1
T-055 | 5. Integration & Testing | User Acceptance Test | Not Started | SH-05: A; SH-10: C; SH-11: R; SH-17: I | 1 | 1 | 1 | 1
T-056 | 5. Integration & Testing | Carrier Connectivity Test | Not Started | SH-08: C; SH-10: I; SH-12: R | 1 | 0 | 1 | 1
T-057 | 5. Integration & Testing | Supplier EDI Test | Not Started | SH-08: R; SH-11: I; SH-13: C | 1 | 0 | 1 | 1
T-058 | 5. Integration & Testing | Gate 5 Review | Not Started | SH-01: A; SH-02: R; SH-05: I; SH-10: C | 1 | 1 | 1 | 1
T-059 | 6. Training & Change | Training Content | Not Started | SH-05: I; SH-11: C; SH-17: R | 1 | 0 | 1 | 1
T-060 | 6. Training & Change | Super-User Training | Not Started | SH-05: C; SH-10: I; SH-11: A; SH-17: R | 1 | 1 | 1 | 1
T-061 | 6. Training & Change | Associate Hiring | Not Started | SH-11: R; SH-16: I; SH-17: C | 1 | 0 | 1 | 1
T-062 | 6. Training & Change | Associate Training | Not Started | SH-05: C; SH-11: A; SH-15: I; SH-17: R | 1 | 1 | 1 | 1
T-063 | 6. Training & Change | Communications | Not Started | SH-02: A; SH-12: C; SH-13: I; SH-17: R | 1 | 1 | 1 | 1
T-064 | 6. Training & Change | Operational Dress Rehearsal | Not Started | SH-05: I; SH-07: C; SH-11: R | 1 | 0 | 1 | 1
T-065 | 6. Training & Change | Gate 6 Review | Not Started | SH-01: A; SH-02: R; SH-11: I; SH-17: C | 1 | 1 | 1 | 1
T-066 | 7. Cutover & Go-Live | Cutover Runbook | Not Started | SH-02: A; SH-06: C; SH-11: I; SH-19: R | 1 | 1 | 1 | 1
T-067 | 7. Cutover & Go-Live | Cutover Rehearsal | Not Started | SH-08: I; SH-09: C; SH-19: R | 1 | 0 | 1 | 1
T-068 | 7. Cutover & Go-Live | Go / No-Go Readiness | Not Started | SH-01: A; SH-02: C; SH-11: I; SH-19: R | 1 | 1 | 1 | 1
T-069 | 7. Cutover & Go-Live | Production Data Load | Not Started | SH-06: C; SH-08: A; SH-09: R; SH-11: I | 1 | 1 | 1 | 1
T-070 | 7. Cutover & Go-Live | Production Code Deploy | Not Started | SH-05: A; SH-06: R; SH-18: C; SH-19: I | 1 | 1 | 1 | 1
T-071 | 7. Cutover & Go-Live | Command Center | Not Started | SH-02: A; SH-11: I; SH-19: R; SH-20: C | 1 | 1 | 1 | 1
T-072 | 7. Cutover & Go-Live | First Inbound Receipt | Not Started | SH-05: I; SH-11: R; SH-12: C | 1 | 0 | 1 | 1
T-073 | 7. Cutover & Go-Live | First Outbound Shipment | Not Started | SH-05: I; SH-11: R; SH-12: C | 1 | 0 | 1 | 1
T-074 | 7. Cutover & Go-Live | Gate 7 Review | Not Started | SH-01: A; SH-02: R; SH-11: I; SH-19: C | 1 | 1 | 1 | 1
T-075 | 8. Hypercare & Close | Hypercare Support | Not Started | SH-05: I; SH-11: C; SH-20: R | 1 | 0 | 1 | 1
T-076 | 8. Hypercare & Close | Volume Ramp | Not Started | SH-07: C; SH-11: R; SH-12: I | 1 | 0 | 1 | 1
T-077 | 8. Hypercare & Close | Financial Close | Not Started | SH-01: I; SH-02: C; SH-16: R | 1 | 0 | 1 | 1
T-078 | 8. Hypercare & Close | Vendor Acceptance | Not Started | SH-07: A; SH-13: R; SH-14: C; SH-16: I | 1 | 1 | 1 | 1
T-079 | 8. Hypercare & Close | Handover to Run | Not Started | SH-06: C; SH-11: I; SH-20: R | 1 | 0 | 1 | 1
T-080 | 8. Hypercare & Close | Lessons Learned | Not Started | SH-01: I; SH-02: R; SH-11: C | 1 | 0 | 1 | 1
T-081 | 8. Hypercare & Close | Gate 8 Review | Not Started | SH-01: A; SH-02: R; SH-16: I; SH-20: C | 1 | 1 | 1 | 1
Assignments per stakeholder |  |  | Total R | 1 | 14 | 1 | 5 | 1 | 5 | 2 | 4 | 5 | 4 | 10 | 4 | 3 | 4 | 1 | 3 | 5 | 3 | 4 | 2
|  |  | Total A | 14 | 5 | 0 | 0 | 6 | 1 | 5 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
|  |  | Total C | 0 | 6 | 2 | 4 | 9 | 14 | 4 | 5 | 1 | 3 | 10 | 3 | 3 | 3 | 3 | 2 | 5 | 1 | 1 | 2
|  |  | Total I | 6 | 8 | 2 | 2 | 10 | 2 | 3 | 2 | 0 | 8 | 18 | 4 | 3 | 0 | 3 | 5 | 2 | 2 | 1 | 0

## Gate Checklists
Completeness Gate Checklists — a phase cannot close while any item is open
Blue = input. Gate status is calculated. The AI Copilot audits these lists before each gate review and lists gaps for the PM to confirm.
Gate | Checklist Item | Owner (ID) | Linked Task(s) | Status | Evidence / Link | Reviewed By | Review Date | Comments
Gate 1 — Initiation complete |  |  |  | Gate status: | PASSED | 6 / 6 done
G1 | Project charter approved by sponsor | SH-02 |  | Complete
G1 | Budget baseline approved and funding released | SH-02 |  | Complete
G1 | Stakeholder register complete with escalation paths | SH-02 |  | Complete
G1 | Steering committee cadence and RAID log established | SH-02 |  | Complete
G1 | Gate checklists and templates loaded into PM tool / AI Copilot | SH-02 |  | Complete
G1 | Vendor shortlist and SOW status confirmed | SH-02 |  | Complete
Gate 2 — Planning & design complete |  |  |  | Gate status: | OPEN — 1 item(s) | 8 / 9 done
G2 | Integrated master plan baselined; critical path identified | SH-02 |  | Complete
G2 | RAID baseline reviewed; every item has owner and due date | SH-02 |  | Complete
G2 | Facility design and permits submitted | SH-02 |  | Complete
G2 | WMS functional and technical design signed off | SH-02 |  | Complete
G2 | Automation design and throughput model approved | SH-02 |  | Complete
G2 | Interface catalogue and data migration strategy approved | SH-02 |  | Complete
G2 | Test strategy approved with exit criteria | SH-02 |  | Complete
G2 | Vendor contracts executed with milestone schedule | SH-02 |  | Complete
G2 | Change and training plan approved | SH-02 |  | Open
Gate 3 — Build complete |  |  |  | Gate status: | OPEN — 8 item(s) | 0 / 8 done
G3 | WMS configuration and customisations complete and unit tested | SH-02 |  | Open
G3 | All interfaces developed and unit tested | SH-02 |  | Open
G3 | Mock data load 1 executed with reconciliation | SH-02 |  | Open
G3 | Equipment manufactured and shipping confirmed | SH-02 |  | Open
G3 | WCS developed; emulation model available | SH-02 |  | Open
G3 | Construction on schedule; no open permit issues | SH-02 |  | Open
G3 | SOPs drafted for every process | SH-02 |  | Open
G3 | Capex within tolerance | SH-02 |  | Open
Gate 4 — Site ready |  |  |  | Gate status: | OPEN — 6 item(s) | 0 / 6 done
G4 | Racking, mezzanine and dock equipment installed | SH-02 |  | Open
G4 | MHE installed and dry-commissioned | SH-02 |  | Open
G4 | Safety inspections passed; certificate of occupancy obtained | SH-02 |  | Open
G4 | Site network, RF devices and printers live | SH-02 |  | Open
G4 | Supervisors hired and onboarded | SH-02 |  | Open
G4 | Yard and dock scheduling ready | SH-02 |  | Open
Gate 5 — Testing complete |  |  |  | Gate status: | OPEN — 7 item(s) | 0 / 7 done
G5 | SIT exit criteria met | SH-02 |  | Open
G5 | Performance test passed at peak volume | SH-02 |  | Open
G5 | Throughput acceptance test ≥ 95% of design rate | SH-02 |  | Open
G5 | UAT signed off by operations | SH-02 |  | Open
G5 | Carrier and supplier EDI tests passed | SH-02 |  | Open
G5 | Zero open Sev-1 defects; Sev-2 plan agreed | SH-02 |  | Open
G5 | Mock data load 2 reconciled | SH-02 |  | Open
Gate 6 — People ready |  |  |  | Gate status: | OPEN — 5 item(s) | 0 / 5 done
G6 | Training content complete for all roles | SH-02 |  | Open
G6 | Super-users certified per process per shift | SH-02 |  | Open
G6 | 100% of go-live associates trained and certified | SH-02 |  | Open
G6 | Operational dress rehearsal passed | SH-02 |  | Open
G6 | Go-live communications issued to stakeholders, suppliers and carriers | SH-02 |  | Open
Gate 7 — Go / No-Go and go-live |  |  |  | Gate status: | OPEN — 7 item(s) | 0 / 7 done
G7 | Cutover runbook approved with rollback plan | SH-02 |  | Open
G7 | Cutover rehearsal completed within window | SH-02 |  | Open
G7 | Readiness assessment green across all workstreams | SH-02 |  | Open
G7 | Production data load reconciled and signed off | SH-02 |  | Open
G7 | Production code deployed and smoke tested | SH-02 |  | Open
G7 | Command center and escalation rota active | SH-02 |  | Open
G7 | First inbound receipt and outbound shipment executed | SH-02 |  | Open
Gate 8 — Hypercare exit and close |  |  |  | Gate status: | OPEN — 7 item(s) | 0 / 7 done
G8 | Hypercare exit criteria met (defects, throughput, inventory accuracy) | SH-02 |  | Open
G8 | Volume ramp on plan | SH-02 |  | Open
G8 | Financial close and benefits baseline complete | SH-02 |  | Open
G8 | Vendor acceptance certificates issued; warranties started | SH-02 |  | Open
G8 | Handover to run organisation complete | SH-02 |  | Open
G8 | Lessons learned published; WBS / RAID / checklist templates updated | SH-02 |  | Open
G8 | All actions closed; project archived | SH-02 |  | Open

## RAID Log
RAID Log — Risks, Assumptions, Issues, Dependencies
Blue = input. Score = Probability × Impact (1–5 each). The AI Copilot proposes new entries from tasks, emails and meetings; the PM confirms them here.
RAID ID | Type | Description | Linked Task | Workstream | Owner (ID) | Raised On | Probability (1-5) | Impact (1-5) | Score | Severity | Mitigation / Response | Due Date | Status | Days Overdue | Source | Last Updated
R-001 | Risk | MHE vendor manufacturing lead time may slip due to component shortages | T-031 | Automation (MHE) | SH-07 | 2026-11-02 | 3 | 5 | 15 | High | Weekly vendor milestone review; identify alternate suppliers for long-lead components; 2-week buffer in plan | 2026-12-28 | Open | 0 | Vendor status email | 2026-10-26
R-002 | Risk | Permit approval delays could push construction start | T-011 | Site Readiness | SH-04 | 2026-11-09 | 2 | 4 | 8 | Medium | Pre-submission meeting with authority; expediter engaged | 2026-11-30 | Open | 0 | Steering committee | 2026-10-26
A-003 | Assumption | ERP will expose standard APIs for inventory sync without customisation | T-016 | Integration & Data | SH-08 | 2026-11-16 | 2 | 3 | 6 | Low | Validate in interface design workshop; raise issue if custom work needed | 2026-12-07 | Open | 0 | Design workshop | 2026-10-26
D-004 | Dependency | WMS SIT depends on WCS emulation model delivery from vendor | T-050 | Testing | SH-10 | 2026-11-30 | 3 | 4 | 12 | Medium | Contractual milestone; emulation delivery tracked as T-032; fallback manual stubs | 2027-04-05 | Open | 0 | AI Copilot — dependency check | 2026-10-26
I-005 | Issue | Wi-Fi survey identified coverage gaps in mezzanine area | T-019 | Infrastructure | SH-18 | 2026-11-23 | 5 | 3 | 15 | High | Add access points to design; revise infrastructure budget | 2026-12-07 | In Progress | 0 | Site survey report | 2026-10-26
R-006 | Risk | Local labour market may not support hiring plan for go-live headcount | T-061 | Operations & Staffing | SH-11 | 2026-11-16 | 3 | 4 | 12 | Medium | Start recruiting 4 weeks earlier; staffing agency backup; referral programme | 2027-05-03 | Open | 0 | Hiring plan review | 2026-10-26
D-007 | Dependency | Carrier EDI testing requires carriers to have TMS lanes configured first | T-056 | Transportation | SH-12 | 2026-12-07 | 2 | 3 | 6 | Low | Sequence T-037 before T-056; confirm carrier readiness monthly | 2027-06-14 | Open | 0 | AI Copilot — meeting notes | 2026-10-26
Formulas:
Days Overdue = IF(OR([Status]="Closed",[Status]="Mitigated",[Status]="Accepted",[Due Date]=""),0,MAX(0,TODAY()-[Due Date]))
Note on B4: Type column drives ID prefix manually: R = Risk, A = Assumption, I = Issue, D = Dependency.

## Action Log
Action Log — decisions and follow-ups from meetings (AI Copilot extracts; PM confirms)
Action ID | Action | Source Meeting / Date | Owner (ID) | Linked Task | Due Date | Status | Days Overdue | Closed On | Notes
A-001 | Confirm alternate supplier options for conveyor drives | Vendor review 20-Oct-26 | SH-13 | T-031 | 2026-11-02 | Open | 0
A-002 | Circulate revised Wi-Fi design with additional access points | Infra design 22-Oct-26 | SH-18 | T-019 | 2026-10-29 | In Progress | 0
A-003 | Book pre-submission meeting with permitting authority | Steering committee 23-Oct-26 | SH-04 | T-011 | 2026-10-30 | Complete | 0 | 2026-10-28
Formulas:
Days Overdue = IF(OR([Status]="Complete",[Status]="Cancelled",[Due Date]=""),0,MAX(0,TODAY()-[Due Date]))